## Cover
B U R N D O W N C H A R T
S D E X A M E N 2 0 2 6
S P R I N T - 1
1 1 - 0 5 - 2 0 2 6
J U R G E N V A N K R A N E N B U R G | D 2 1 4 2 3 8
D Y L A N E X T E R S | D 3 2 0 7 5 7
F L O R I A N G E E N S E | D 3 0 3 4 7 3

## Taken
User Stories & Team Statestieken | [10 empty] | Project start: | 2026-05-11
User story lijst |  |  |  |  | Teamleden Statestieken
Klaar | US Nr. | Grootte | Toegewezen aan | Afrond Datum | Naam | Toegewezen Taken | Afgeronde Taken | Afgerond Percentage | Gemiddlede Taak Grootte | Totale Tijd Max P.P. | Totale Tijd Gem P.P. | Totale Tijd Min P.P.
FALSE | 1 | M | Jurgen |  | Jurgen | 3 | 0 | 0% | XL | 0.5625 | 0.45833 | 0.35417
FALSE | 2 | S | Kaas |  | Kaas | 3 | 0 | 0% | XL | 0.45833 | 0.375 | 0.29167
FALSE | 3 | S | Maarten |  | Maarten | 1 | 0 | 0% | S | 0.041667 | 0.03125 | 0.020833
FALSE | 4 | L | Jurgen |  | Ahmed | 3 | 0 | 0% | XL | 0.60417 | 0.5 | 0.39583
FALSE | 5 | XXL | Jurgen |  |  | 100% | 0% |  |  | 0.41667 | 0.34115 | 0.26562
FALSE | 6 | S | Ahmed
FALSE | 7 | M | Kaas
FALSE | 8 | XXL | Ahmed
FALSE | 9 | XL | Ahmed
FALSE | 10 | XXL | Kaas
0 | 10 | XL | 4 | 0%
Formulas:
Afrond Datum = IF(BurndownTasks[[#This Row],[Klaar]]=TRUE, IF(BurndownTasks[[#This Row],[Afrond Datum]]="", TODAY(), BurndownTasks[[#This Row],[Afrond Datum]]), "")
Totale Tijd Max P.P. = SUM(TeamStats5[Totale Tijd Max P.P.]) / BurndownTasks[[#Totals],[Toegewezen aan]]
Totale Tijd Gem P.P. = SUM(TeamStats5[Totale Tijd Gem P.P.]) / BurndownTasks[[#Totals],[Toegewezen aan]]
Totale Tijd Min P.P. = SUM(TeamStats5[Totale Tijd Min P.P.]) / BurndownTasks[[#Totals],[Toegewezen aan]]
Note on D5: XXS .......... 0 min - 10 min XS ........... 10 min - 30 min S ............ 30 min - 1 hour M ............ 1 hour - 2 hour L ............ 2 hour - 3 hour 30 min XL ........... 3 hour 30 min - 5 hour 30 min XXL .......... 5 hour 30 min - 8 hour
Note on F5: automatically filled in
Note on M5: In hours and minutes
Note on N5: In hours and minutes
Note on O5: In hours and minutes
Note on I10: Percentage of tasks assigned out of all tasks
Note on J10: Percentage of tasks finished out of all tasks
Note on M10: Maximum hours per person
Note on N10: Average hours per person, should not be more than 40 hours
Note on O10: Minimum hours per person.
Note on B16: Counts the number of tasks that are finished
Note on C16: Counts the number of tasks
Note on D16: Average size of the project / all tasks
Note on E16: Number of unique candidates
Note on F16: Percentage of tasks finished

## Afbrand Grafiek
Afbrand Grafiek
User Stories
Dag | Ideaal | Werkelijk
Dag 1 | 10 | 10
Dag 2 | 8 | 10
Dag 3 | 7 | 10
Dag 4 | 5 | 10
Dag 5 | 3 | 10
Dag 6 | 2 | 10
Rest | 0 | 10
Note on C5: Amount of tasks still left
Note on D5: Amount of tasks still left

## Overige Data
Overige Data
Size & Time Data
Grootte | Punten | Werk Minuten Gem | Werk Minuten Min | Werk Minuten Max | Geschatte werktijd
XXS | 1 | 5.5 | 1 | 10 | 0 min - 10 min
XS | 2 | 20 | 10 | 30 | 10 min - 30 min
S | 3 | 45 | 30 | 60 | 30 min - 1 uur
M | 5 | 90 | 60 | 120 | 1 uur - 2 uur
L | 8 | 165 | 120 | 210 | 2 uur - 3 uur 30 min
XL | 13 | 270 | 210 | 330 | 3 uur 30 min - 5 uur 30 min
XXL | 21 | 405 | 330 | 480 | 5 uur 30 min - 8 uur